## Product Log
CSCE 315-100 Programming Studio
Team 6 - Project 2 & 3 SCRUM Product Log
Iteration 1
Id | Story | Labels | Iteration | Iteration Start | Iteration End | Story Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Owned By | Description | URL | Comment | Comment | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status
31125957 | the board state can initialize at the game start |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-12 |  | William Guerra | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31125957
31126137 | the player may specify a move using letters and numbers |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-13 |  | William Guerra | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31126137
31126389 | the board can update after every player move |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-13 | 2012-06-13 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31126389
31126213 | the game can let the user know if his input is a valid move |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-13 | 2012-06-13 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31126213
31190197 | Enable/fix turn-based gameplay |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-13 |  | William Guerra | William Guerra |  | http://www.pivotaltracker.com/story/show/31190197
31125417 | a player can choose to play as black or white |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-13 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125417
31191531 | the board can display if it is black's move or white's move |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31191531
31232613 | game always starts with black player |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-14 | 2012-06-14 |  | William Guerra | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31232613
31125471 | a player can undo his last move |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31125471
31125613 | a player can redo a move he's undone |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31125613
31126427 | when a game ends the board can determine the winner |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31126427 | I haven't found any bugs yet for when the game ends. (Phillip Ells - Jun 14, 2012)
31191473 | the board can display what the next available moves are |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31191473
31127289 | iron out the kinks for GitHub or use SVN |  | 1 | 2012-06-11 | 2012-06-17 | chore |  | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | Daniel Tan | FINISH TODAY (6/12/12) | http://www.pivotaltracker.com/story/show/31127289
31244757 | Writing error log 1 for Daniel's function |  | 1 | 2012-06-11 | 2012-06-17 | bug |  | accepted | 2012-06-14 | 2012-06-14 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31244757
31125201 | a player can exit the game |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125201
31234851 | make a nicer, more organized gameLoop() |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-14 | 2012-06-14 |  | William Guerra | William Guerra |  | http://www.pivotaltracker.com/story/show/31234851
31259537 | Handle draw scenario |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-14 | 2012-06-14 |  | Phillip Ells | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31259537
31126399 | the board can check to see if the game is over |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-13 | 2012-06-14 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31126399
31258567 | Writing more bugs and errors to the error log |  | 1 | 2012-06-11 | 2012-06-17 | bug |  | accepted | 2012-06-14 | 2012-06-14 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31258567
31248757 | a player can lose a turn if he has no valid moves |  | 1 | 2012-06-11 | 2012-06-17 | feature | 1 | accepted | 2012-06-14 | 2012-06-14 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31248757
31233839 | extensive bug testing |  | 1 | 2012-06-11 | 2012-06-17 | bug |  | accepted | 2012-06-14 | 2012-06-14 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31233839
31126547 | Game mechanics deliverable (2 human players) |  | 1 | 2012-06-11 | 2012-06-17 | release |  | accepted | 2012-06-13 | 2012-06-15 | 2012-06-15 | Daniel Tan |  |  | http://www.pivotaltracker.com/story/show/31126547
31127325 | start development document & report |  | 1 | 2012-06-11 | 2012-06-17 | bug |  | accepted | 2012-06-13 | 2012-06-15 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31127325
31241145 | Implement test telnet server code |  | 1 | 2012-06-11 | 2012-06-17 | feature | 3 | accepted | 2012-06-14 | 2012-06-16 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31241145 |  |  | Establish a connection to the server | completed | Send and receive data through connection | not completed
31240865 | Implement random position AI |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-14 | 2012-06-17 |  | Phillip Ells | William Guerra |  | http://www.pivotaltracker.com/story/show/31240865
Iteration 2
31191645 | the board can display the number of points for both black and white |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-19 |  | William Guerra | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31191645 | I didnt start it, but I had to to make this comment: it doesnt update (correctly) until next is entered (William Guerra - Jun 15, 2012)
31125355 | a player can choose the AI difficulty |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-19 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125355 | Its very sassy (William Guerra - Jun 15, 2012) | Well, I lost it, but it is now rewritten. SLightly less sassy (William Guerra - Jun 16, 2012)
31327633 | Determine how many pieces are flipped for a move |  | 2 | 2012-06-18 | 2012-06-24 | feature | 3 | accepted | 2012-06-16 | 2012-06-19 |  | William Guerra | William Guerra |  | http://www.pivotaltracker.com/story/show/31327633
31481641 | Determine how many opponent moves are available after a move |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-19 | 2012-06-19 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31481641
31338531 | Design general tree traversal |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-17 | 2012-06-19 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31338531 | Design for min mobility AI (Daniel Tan - Jun 17, 2012) |  | Print out tree for a set search depth | not completed | Count the total opponent moves | not completed | Store the path of the lowest number of opponent moves | not completed
31449087 | AI can minimize opponent's mobility |  | 2 | 2012-06-18 | 2012-06-24 | feature | 3 | accepted | 2012-06-19 | 2012-06-19 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31449087
31481935 | More game engine testing |  | 2 | 2012-06-18 | 2012-06-24 | chore |  | accepted | 2012-06-19 | 2012-06-21 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31481935
31330693 | the game engine can run on a server |  | 2 | 2012-06-18 | 2012-06-24 | feature | 3 | accepted | 2012-06-16 | 2012-06-21 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31330693
31240065 | Additional: Play again dialogue after game ends |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-14 | 2012-06-21 |  | Phillip Ells | William Guerra |  | http://www.pivotaltracker.com/story/show/31240065
31125339 | a player can turn the display on |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-21 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125339
31125333 | a player can turn the display off |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-21 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125333
31481815 | the printouts of the game are cleaner and contained in one place (optimize outputs) |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-19 | 2012-06-21 |  | William Guerra | William Guerra |  | http://www.pivotaltracker.com/story/show/31481815
31481371 | each build name will have names rhyming with minnow |  | 2 | 2012-06-18 | 2012-06-24 | chore |  | accepted | 2012-06-19 | 2012-06-21 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31481371
31483333 | fix an issue with undo in hard AI |  | 2 | 2012-06-18 | 2012-06-24 | bug |  | accepted | 2012-06-19 | 2012-06-21 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31483333
31338411 | AI Final Release |  | 2 | 2012-06-18 | 2012-06-24 | release |  | accepted | 2012-06-17 | 2012-06-21 | 2012-06-22 | Daniel Tan |  |  | http://www.pivotaltracker.com/story/show/31338411
31639607 | Finalize Project 2 report |  | 2 | 2012-06-18 | 2012-06-24 | chore |  | accepted | 2012-06-22 | 2012-06-23 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31639607 |  |  | Maybe add 4 sub-sections giving more detail on each AI algorithms | not completed | Double check with Phillip and William if this section needs any updates given the final server design | completed | To be completed with newly added functions for reverse.java | completed | To be completed - telnetReversi.java function list and descriptions | completed | Design Thoughts and Considerations, Problems and Solutions, and Lessons Learned: | completed
31701789 | Final Version Release |  | 2 | 2012-06-18 | 2012-06-24 | release |  | accepted | 2012-06-23 | 2012-06-23 | 2012-06-25 | Daniel Tan |  |  | http://www.pivotaltracker.com/story/show/31701789
Iteration 3
31780081 | link play button to gameboard |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-25 | 2012-06-26 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31780081
31780101 | add pop up menu |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-25 | 2012-06-26 |  | Daniel Tan | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31780101
31780113 | create basic gameboard layout |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-25 | 2012-06-26 |  | Daniel Tan | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31780113
31780127 | Create togglebutton |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-25 | 2012-06-26 |  | Daniel Tan | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31780127
31801845 | create splash screen |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-26 | 2012-06-27 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31801845
31800853 | ReversiRules functions can affect gameboard activity |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-26 | 2012-06-27 |  | Daniel Tan | Daniel Tan | ReversiRules can call the Gameboard instance and the Gameboard functions | http://www.pivotaltracker.com/story/show/31800853
31800859 | add buttons and pieces to gameboard xml |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-26 | 2012-06-27 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31800859
31800823 | pieces can display a 3D flip animation |  | 1 | 2012-06-25 | 2012-07-01 | feature | 3 | accepted | 2012-06-26 | 2012-06-27 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31800823
31874585 | Complete Game selection art |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-26 | 2012-06-27 |  | William Guerra | William Guerra | buttons, background | http://www.pivotaltracker.com/story/show/31874585
31874573 | complete Gameboard art |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-26 | 2012-06-27 |  | William Guerra | William Guerra | pieces, buttons, background "board" | http://www.pivotaltracker.com/story/show/31874573
31874561 | Complete Main menu art |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-26 | 2012-06-27 |  | William Guerra | William Guerra |  | http://www.pivotaltracker.com/story/show/31874561
31780605 | Project 3-Part 1: Design doc, SCRUM log, & XML design (for game statistics). |  | 1 | 2012-06-25 | 2012-07-01 | release |  | accepted | 2012-06-25 | 2012-06-27 | 2012-06-27 | Daniel Tan |  |  | http://www.pivotaltracker.com/story/show/31780605
31842027 | Complete game mode menu |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-26 | 2012-06-27 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31842027
31842065 | Complete main menu |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-26 | 2012-06-27 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31842065
31923373 | Gameboard tracks the current score of each player. |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-27 | 2012-06-28 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31923373
31922613 | Implement redo |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-27 | 2012-06-28 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31922613
31922593 | Implement undo |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-27 | 2012-06-28 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31922593
31922939 | Implement AI |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-27 | 2012-06-28 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31922939
31941311 | create options menu |  | 1 | 2012-06-25 | 2012-07-01 | feature | 2 | accepted | 2012-06-27 | 2012-06-28 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31941311
31941355 | link high scores page |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-27 | 2012-06-28 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31941355
31941331 | create about page |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-27 | 2012-06-28 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31941331
32006251 | read/write test case to SD card |  | 1 | 2012-06-25 | 2012-07-01 | feature | 3 | accepted | 2012-06-28 | 2012-06-29 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/32006251
31874549 | Complete High scores art |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-26 | 2012-06-30 |  | William Guerra | William Guerra | background and a back button | http://www.pivotaltracker.com/story/show/31874549
32036857 | Player can start as black or white |  | 1 | 2012-06-25 | 2012-07-01 | feature | 1 | accepted | 2012-06-29 | 2012-06-30 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/32036857
32064259 | Implement read and write to xml on SD |  | 1 | 2012-06-25 | 2012-07-01 | feature | 3 | accepted | 2012-06-29 | 2012-07-01 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/32064259
32073019 | finish about pages |  | 1 | 2012-06-25 | 2012-07-01 | feature | 0 | accepted | 2012-06-30 | 2012-07-01 |  | William Guerra | Phillip Ells |  | http://www.pivotaltracker.com/story/show/32073019
31923097 | Gameboard Menu Button will ask 'are you sure?' |  | 2 | 2012-07-02 | 2012-07-08 | feature | 1 | accepted | 2012-06-27 | 2012-07-02 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31923097
31923197 | New Game will ask 'are you sure'? |  | 2 | 2012-07-02 | 2012-07-08 | feature | 1 | accepted | 2012-06-27 | 2012-07-02 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31923197
31923349 | Gameboard can print out informative text at each game state |  | 2 | 2012-07-02 | 2012-07-08 | feature | 1 | accepted | 2012-06-27 | 2012-07-02 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31923349
31874557 | Complete Win game graphics |  | 2 | 2012-07-02 | 2012-07-08 | feature | 1 | accepted | 2012-06-26 | 2012-07-02 |  | William Guerra | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31874557
32080107 | Finish project 3 report |  | 2 | 2012-07-02 | 2012-07-08 | chore |  | accepted | 2012-07-01 | 2012-07-02 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/32080107
32080121 | Project 3 Final Deliverable |  | 2 | 2012-07-02 | 2012-07-08 | release |  | unstarted | 2012-07-01 |  | 2012-07-02 | Daniel Tan |  |  | http://www.pivotaltracker.com/story/show/32080121

## Burndown Charts
Sprint 1 Burndown Chart | Sprint 2 Burndown Chart | Sprint 3 - Part 1 Burndown Chart | Sprint 3 - Part 2 Burndown Chart